## Slide 1
ShipReX (Rex Software) — stage plot
Set 7:15–7:40 pm · soundcheck 6:00 pm · contact on the day: Scott Warren
UPSTAGE (back wall)
AUDIENCE
◀ house left (stage right)
house right (stage left) ▶
DW kit · ch 1–10
Simon
riser 2.4 × 1.8 m
Fender · mic ch 13
Scotty
Ampeg · not mic'd
Vox AC30 · mic ch 15
Thiago
Keys · Daniel · TBC
DI ch 19/20
Scotty
guitar (from
song 2)
Scott W
vox
Sophie
erhu
Erhu DI · ch 18
Kirra
bass
Bass DI · ch 11
Hamish
vox
Thiago
guitar
Mindy
vox
Elle
vox
Lil
vox
Vox 1 · ch 21
Vox 2 · ch 22
Vox 3 · ch 23
Vox 4 · ch 24
Backline
Player
Vocal mic
DI box
Keys
Laptop / screen
In-ears / wireless
Dashed = not used this set
1 m · all to scale; DI boxes and mic stands slightly enlarged

## Slide 2
ShipReX (Rex Software) — patch and notes
Set 7:15–7:40 pm · soundcheck 6:00 pm · contact on the day: Scott Warren
Ch | Input | Who and notes
1–10 | Drum kit | Simon
11 | Bass DI | Kirra, DI only (no cab mic)
13 | Gtr 1 (Fender) | Scotty, joins from song 2
15 | Gtr 2 (Vox AC30) | Thiago
18 | Instrument DI | Sophie, erhu pickup
19/20 | Keys L/R | Daniel
21 | Vox 1 | Scott W: lead on songs 3 and 4
22 | Vox 2 | Hamish: lead on songs 1, 2, 5 and 6
23 | Vox 3 | Mindy and Elle share
24 | Vox 4 | Lil
Not used this set: ch 12, 14, 16, 17, 25, 26, 27, 28. Ch 31/32 are the crowd mics, for the recording only.
Monitors and in-ears
No in-ear feeds requested.
Screen and playback
None.
Notes and to confirm
Stage layout is as they stood in Brisbane. Is Daniel bringing a keyboard, or using the Korg Kronos? Lighting for Mustang Sally (new for Sydney); the other lighting notes are carried over from Brisbane.

## Slide 3
ShipReX (Rex Software) — the set
Set 7:15–7:40 pm · soundcheck 6:00 pm · contact on the day: Scott Warren
Running time: 24:25 planned, in a 25-minute slot. No walk-on or between-song details given.
Step | Song, or what happens | Length | On stage · lead · moves | Screen · playback | Lighting
Song 1 | Uprising — Muse (opens with 30 s of Careless Whisper on erhu) | 6:00 | Everyone except Scotty (guitar). Lead: Hamish (Vox 2) |  | Dark, spotlight on the erhu to begin. Blackout on the last erhu note, then hit the full band in deep red on the Uprising riff. Moody red through the verses with a slow pulse on the stomp beat, brighter white hits on the choruses
Song 2 | Espresso — Sabrina Carpenter | 3:00 | Everyone (Scotty joins on guitar). Lead: Hamish (Vox 2) |  | Bright and poppy: full warm wash, yellows, oranges and hot pink. No dark moments. Colour sweep or mirror ball on each chorus; keep the crowd lit
Song 3 | Dumb Things — Paul Kelly | 3:00 | Everyone. Lead: Scott W (Vox 1) |  | Warm white pub-rock wash, even and front-lit so faces are visible. Lift the wash and bring up the crowd for the singalong choruses
Song 4 | Mustang Sally — Wilson Pickett | 4:10 | Everyone. Lead: Scott W (Vox 1) |  | Not given yet
Song 5 | Everlong — Foo Fighters | 4:30 | Everyone. Lead: Hamish (Vox 2) |  | Cool blues and purples on the verses, slam to bright white on every chorus. Drop to a single colour for the quiet bridge, then full blast for the last chorus
Song 6 | Covered in Chrome — Violent Soho | 3:45 | Everyone. Lead: Hamish (Vox 2) |  | Closer, go big: hot white and red, strobes on the chant, everything on for the outro. Hard blackout on the final hit